ACTION BY KEY: PR= President, OM= Operations Manager, SM= Systems Manager, SEC= Secretary, PO= Public Officer, TM= Track Manager includes ATM= Assistant TM, FC= Finance Co-ordinator, TR= Treasurer, IM= Infrastructure Manager, IA= Internal Auditor, RM=Rollingstock Manager, TL= Team Leader

Risks in OTHR operation: Public Display at Oberon Station   	Affects objective Safely manage the  public during open displays at Oberon 
Document Date: 16/02/2010. Reviewed: 08/09/12	Drafted by: ATM, IM,CM          Assessed by: SM

References: TB- 013, TB-017. TB-018

| Risk No. | Task & Hazard What can cause Harm? | Risk What could happen? (Triggers)” | Inherent Risk | Controls How could it be fixed? | Residual Risk | ALARP | Finding: Issues? Problems? Adopt? | Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Lik. | Cons | Risk |  | Lik. | Cons | Risk | ? |  | By | When |
| 1 | Poor Planning. | Failure to properly plan may lead to avoidable risks and possible injury to workers and contractors Triggered by: poor planning failure to follow procedures lack of expertise short cuts poor supervision | 3 | 4 | 7 | Meeting to consider: Detailed planning. Clear procedures. Provision of adequate supervision. | 2 | 2 | 4 | y | Meeting to be held to co-ordinate the project and consider options such as effective Risk Assessment | tl SEC | Week before |
| 2 | Weather issues - consider the possibility of rain. | Increased risk of slip, trip & fall. | 3 | 3 | 6 | Distribute crusher dust in risky areas. Barrier slippery areas with safety cones & or tape. Warn visitors. | 2 | 2 | 4 | y | Adopt all. | tl IM | Prior to event |
| 3 | High platform and loading ramp. | People may fall off these areas. | 4 | 5 | 9 | Temporary safety tape barrier for the platform and to exclude access to the loading ramp. | 1 | 3 | 4 | Y | Adopt. | CEO | Prior to event |
| 4 | Multiple rails and tripping points. | Slips Tripping Falling | 4 | 3 | 7 | Restricting public to safe areas by means of temporary safety tape barrier. | 1 | 2 | 3 | y | Adopt | TL | Prior to event |
| 5 | Uneven surfaces. | Slips Tripping Falling | 4 | 3 | 7 | Fill uneven surfaces. | 1 | 2 | 3 | y | Adopt. | TL | Prior to event |
| 6 | Protruding parts on wagons. | Injury to visitors Slip / trip / fall | 4 | 5 | 9 | Restricting public to safe areas by means of temporary safety tape barrier. | 2 | 3 | 5 | y | Adopt | TL | Prior to event |
| 7 | Climbing on rolling stock. | Falls may cause injury or death | 5 | 5 | 10 | Restricting public to safe areas by means of temporary safety tape barrier.. | 2 | 4 | 6 | y | Adopt. Volunteers need to be vigilant. | TL | Lift -2 days |
| 8 | Power leads to displays. | Electrocution Trip hazard | 4 | 5 | 9 | Raise the leads to a safe height (2.4m). Neat installation. No loose leads on the ground. | 2 | 4 | 6 | y | Adopt. Advise display managers. | TL | Prior to event |
| 9 | Hot water urn. | Urn may tip over causing burns. | 5 | 5 | 10 | Urn located out of public access. Located on a secure table. | 1 | 3 | 4 | y | Adopt. | cm | At Event |
| 10 | Food Handling | Spread of Infection Cuts Burns Spills | 3 | 3 | 6 | Hand washing, gloves, surface cleaning, personal hygiene Staff experience Food covers House cleaning | 1 | 1 | 2 | Y | Adopt all. Mitigated by using volunteers with considerable experience in food handling. | CM | At Event |
| 11 | Sun and heat – workers. | Sunburn | 3 | 4 | 7 | Limit exposure and provide sunscreen. | 1 | 2 | 3 | y | Adopt. | TL | At Event |
| 12 | Hygiene and cleanliness issues. | Lack of toilet facility. Disease transmission. | 3 | 3 | 6 | Provide temporary toilet. Hand washing facility nearby. | 1 | 1 | 2 | y | Adopt. | TL | Prior to event |
| 13 | Erection of marquee / tents. |  | 3 | 5 | 8 | Avoid pinch points Care when driving pegs Care with guy ropes. | 3 | 5 | 8 | ? | Adopt. Advise display managers. | CEO SEC TL | Prior to event |
| 14 | Snakes | Snake bite Fright | 3 | 4 | 7 | Warning sign Observant volunteers. | 2 | 3 | 5 | Y | Adopt but increased activity likely to lessen risk. | TL | At Event |
| 15 | Obstacles. | Impedes access and movement Slips, trips & falls Falls from platform | 4 | 4 | 8 | Clear walkways and movements paths of objects likely to be obstacles. | 1 | 2 | 3 | y | Tables in front of the station building are one identified problem. Relocate tables to less dangerous areas Adopt. | TL | At Event |

ACTION BY KEY: CEO= President, OM= Operations Manager, SM= Systems Manager, SEC= Secretary, PO= Public Officer, TM= Track Manager includes ATM= Assistant TM, FC= Finance Co-ordinator, TR= Treasurer, IM= Infrastructure Manager, IA= Internal Auditor, RM=Rollingstock Manager

SIGNATURE SHEET - Risk Assessment for: ………………………………………………………………….……. (brief description)
Risk Assessment associated with OTHR operation described above.                          Date of Operation: …… /……. /2…….

| Risk No. | Hazard What can go wrong? | Risk What could happen? | Inherent Risk | Controls How could it be fixed? | Residual Risk | ALARP | Finding: Issues? Problems? Adopt? | Action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Lik. | Cons | Risk |  | Lik. | Cons | Risk | ? |  | By | When |
| ALL | As described above. | I have discussed and understand the risks. | I will implement the Controls described above to the best of my ability so that the Risk is managed so that it is AS LOW AS REASONABLY PRACTICAL. | Note any issues you have with the Risks, Management or Controls. |
| OPERATING CREW. The operating crew on the day are requested to sign this document indicating that they have READ and UNDERSTOOD the RISKS and CONTROLS associated with this operation. | NAME (Print) ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… | POSITION (Task) TEAM LEADER ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… | signature ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… | COMMENT ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. |