ACTION BY KEY: PR= President, OM= Operations Manager, SM= Systems Manager, SEC= Secretary, PO= Public Officer, TM= Track Manager, FM= Finance Manager, TR= Treasurer, IM= Infrastructure Manager, IA= Internal Auditor, RM=Rollingstock Manager, TL=Team Leader

Risks in OTHR operation: Oberon Yard Crane Lift Loco’s to Rail     Affects objective: Safely unload locos to RAIL & move to temporary storage area.
Document Date  04/01/11 	Drafted by:  ID         Assessed by: …………………..………

| Risk No. | Hazard What can go wrong? | Risk What could happen? | Inherent Risk |  |  | Controls How could it be fixed? | Residual Risk |  |  | ALARP | Finding: Issues? Problems? Adopt? | Action |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | L’hd. | Cons | Risk |  | L’hd. | PEC | Risk | ? |  | By | When |
|  | PREPARING LOCO’s FOR LIFT |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | CRANE Unqualified and/or uninsured operator. | Injury or death to personnel and property damage. | 2 | 4 | 4 | * Independent check by OTHR on qualifications, currency and insurance. | 1 | 3 | 2 | y | Adopt. File copies with DC. | PR SEC RM | Lift -1 week |
| 2 | CRANE Unsatisfactory access for uplift. | Damage to crane or property. | 3 | 6 | 6 | * Pre-inspection of site by OTHR & crane rep. | 1 | 3 | 2 | y | Adopt. PR is included as the crane operator. This site is well known to OTHR teams. | PR tm RM | Lift -1 week |
| 3 | CRANE Unsafe footing due to underground services, trenches or embankments. | Crane may be damaged or topple causing injury to crew or bystanders. | 3 | 6 | 6 | * Check with Council & authorities re. location of services. * Qualified operator. | 2 | 2 | 2 | y | Adopt both combined with cleared work area - essential personnel only. Services have been previously located. | PR tm | Lift -1 week |
| 4 | CRANE Unsafe footing due to heavy rain & soft ground. | Crane may be damaged or topple causing injury to crew or bystanders. | 3 | 6 | 6 | * Qualified operator. * Consider weather and cancel or re-locate lift if in doubt. | 2 | 2 | 2 | n | Cancel or relocation preferred. | PR tm RM | Lift -2 days |
| 5 | CRANE Overhead obstructions. | Crane may hit power lines, cables, poles or buildings causing injury to crew or workers. | 3 | 6 | 9 | * Qualified operator. * OTHR to provide an independent spotter. | 1 | 2 | 2 | y | Adopt both. Arrange communication between spotter & operator. | PR tm RM | Lift day |
| 6 | CRANE Inappropriate lift crane. Incorrect or uncertified lifting gear. | Dropped load, Damage to loco. Injury to workers. | 3 | 3 | 4 | * Prior approval of equipment and load certification * All slings to be rated; weight of lift to be established and verified | 1 | 2 | 2 | y | Adopt, combined with cleared work area - essential personnel only. | PR tm RM | Lift day |
| 7 | CRANE Incorrect spreader bars. | Dropped load. Damage to loco. Injury to workers. | 3 | 3 | 6 | * Ensure correct spreaders by checking with crane op. | 1 | 2 | 3 | y | Adopt combined with cleared work area - essential personnel only. | PR tm RM | Lift day |
| 8 | PREPARATION FOR NEXT STAGE Loco may roll away. | Loco may roll away when released from crane | 3 | 6 | 7 | * Apply hand brake. * Have wheel chocks ready. * Clamp rail stop to down gradient side. * Use a sleeper across the line if in doubt. | 2 | 3 | 4 | y | Adopt all controls - additional sleepers could be used between loco’s if necessary. | tl RM TM |  |
|  | LIFTING LOCO’S |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | LIFTING Personnel encroach upon safety zone. | Injury to public, OTHR workers and unloading crew. | 2 | 5 | 7 | * Briefing prior to start. * Security barriers. * Crowd control personnel. * Evacuation point marked. | 1 | 2 | 3 | y | Combination of all controls. | tl tm RM | Lift day |
| 10 | LIFTING Unauthorised entry to safety zone. | Injury to intruder. | 3 | 5 | 8 | * Operations within secured yard area. * Police supervision if required. | 2 | 2 | 2 | n | Minimise by requesting Police supervision in advance if problematical. | tl | Lift -2 weeks |
| 11 | LIFTING Unloading crew hit by load. | Injury to crew. | 3 | 5 | 8 | * Briefing prior to start. * Clear hazards from work area. * Wear PPE including hard hat. | 2 | 2 | 4 | y | Adopt all controls. | tl tm RM | Lift day |
| 12 | LIFTING Holes, Uneven surfaces Tripping hazards. | Trips, falls and injury | 3 | 3 | 7 | * Fill holes. * Level uneven surfaces. * Remove all obstacles. | 2 | 2 | 4 | y | Adopt all controls. | tl tm | Lift -1 week |
| 13 | LIFTING Load falls | Injury or death to crew. | 3 | 5 | 8 | * No personnel to be under the load at any time. * All unnecessary personnel to be kept clear. | 1 | 1 | 2 | y | Adopt. Crane operator needs to supervise lifting team. | tl tm RM | Lift day |
|  | LOCATING LOCO’S TO RAIL |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | LOWERING TO RAIL Loco swings out of control. | Injury or death to crew. Damage to property or crane. | 3 | 3 | 6 | * Briefing prior to start. * Wear PPE including gloves and hard hat. * A crew of 2 to 4 people on “tag lines” to prevent swinging. * Operation to be carried out at a slow and steady pace. * Tag line crew to maintain contact with crane driver using a spotter if need be. | 2 | 2 | 4 | y | Adopt all controls. (tag lines are ropes attached to each corner or diagonally opposite corners of the loco). | TL tm RM | Lift day |
| 15 | LOWERING TO RAIL Locating onto rails. | Injury to crew. Pinch points. | 3 | 3 | 6 | * Briefing prior to start. * Wear PPE including gloves and hard hat. * Last stage of lowering to be at extreme low speed. * Keep clear of rail / wheel junction. | 1 | 1 | 2 | y | Adopt all controls. | TL tm RM | Lift day |
|  | MOVING LOCO’S TO SECURE STORAGE POSITION |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 | Competent train crew not available | Failure to start or move Loco’s | 3 | 3 | 6 | Train crew identified and current documentation sighted by OTHR | 1 | 1 | 2 | Y | Adopt | RM OM | Lift Day |
| 17 | Authority to Operate form not completed | Loco’s cant proceed | 2 | 3 | 4 | Forms are available and authorising persons present to sign off | 1 | 1 | 2 | Y | Adopt | OM SEC |  |
| 18 | Track not clear | Damage to loco. Injury to workers. Damage to property. | 3 | 3 | 8 | * Inspect track before operation. * Driver has clear view of track | 1 | 1 | 2 | y | Adopt. | OM | Lift day |
| 19 | Loco wont stop | Damage to loco. Injury to workers. Damage to property. | 3 | 3 | 6 | * Test loco brakes prior to movement & repair if ineffective. * Fit effective backup stops -sleepers bolted across the line with backup sleepers on the line. | 1 | 1 | 2 | y | Adopt all controls. Gradient is 1:174 towards Albion St. | TL tm RM | Lift day |
|  | SECURE STORAGE |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 | LOCO’S STORED Runaway due to missing or ineffective chocks or restraints. | Damage to loco. Injury or death to people including crushing during movement. A runaway could breach the fence and cross Albion St with disastrous consequences. Damage to property. | 3 | 3 | 6 | * Fit effective restraints -sleepers bolted across the line with backup sleepers on the line. * Set & lock catch points and derailers between r/stock and Albion Street. * Apply loco handbrake & repair if ineffective. * Lock handbrakes if possible. | 1 | 1 | 2 | y | Adopt all controls. Gradient is 1:174 towards Albion St. | TL RM | Unload day |
| 20 | LOCO’S SECURED Access to the locos will be by authorised personnel only. There will be no access from platforms | Injury to personnel as a result of falling from loco. Possible injury or death to workers or visitors. Vandalism. | 3 | 3 | 6 | * Barriers will be needed at loco access points. * Security cameras and fences in place. | 2 | 3 | 5 | y | Adopt all controls. | RM | Post Unload day |
|  | The following plan indicates where it is proposed to locate the 2 loco’s onto the line. |  |  |  |  |  |  |  |  |  |  |  |  |
|  | LOCO’s formatting of the pull quote text box.] |  |  |  |  |  |  |  |  |  |  |  |  |

ACTION BY KEY: PR= President, OM= Operations Manager, SM= Systems Manager, SEC= Secretary, PO= Public Officer, TM= Track Manager includes ATM= Assistant TM, FC= Finance Co-ordinator, TR= Treasurer YET TO BE APPOINTED: IM= Infrastructure Manager, IA= Internal Auditor, RM=Rollingstock Manager

SIGNATURE SHEET - Risk Assessment for: Unloading Loco’s at Oberon Yard after Movement from Storage. (brief description)
Risk Assessment associated with OTHR operation described above.                          Date of Operation:   /01 /2011

| Risk No. | Hazard What can go wrong? | Risk What could happen? | Inherent Risk |  |  | Controls How could it be fixed? | Residual Risk |  |  | ALARP | Finding: Issues? Problems? Adopt? | Action |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | L’hd. | Cons | Risk |  | L’hd. | Cons | Risk | ? |  | By | When |
| ALL | As described above. | I have discussed and understand the risks. |  |  |  | I will implement the Controls described above to the best of my ability so that the Risk is managed so that it is AS LOW AS REASONABLY PRACTICAL. |  |  |  |  | Note any issues you have with the Risks, Management or Controls. |  |  |
| OPERATING CREW. The operating crew on the day are requested to sign this document indicating that they have READ and UNDERSTOOD the RISKS and CONTROLS associated with this operation. |  | NAME (Print) ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… ………………………………………………… |  |  |  | POSITION (Task) ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… | signature ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… ………………………… |  |  |  | COMMENT ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. ………………………………………. |  |  |